## Sheet1
Activity | Expected Start Date | Expected end date | Actual Start Date | Actual end date
SRS Release | 3rd October | 9th October | 3rd October | 9th October
Design | 4th October | 4th October | 4th October | 4th October
Coding | 5th October | 6th October | 5th October | 6th October
UT Plan | 7th October | 8th October | 7th October | 8th October
UT | 8th October | 8th October | 8th October | 8th October
IT Plan | 8th October | 8th October | 8th October | 8th October
IT | 8th October | 8th October | 8th October | 8th October
Sprint Demo | 19th October | 19th October | 19th October | 19th October